# MULOO DEPLOYOS

Audit Status Update

Prepared for Jarrud  ·  29 April 2026

# 1. Executive summary

Twelve days after the audit, the Week 1 stabilise list is shipped and a meaningful slice of the Week 2-6 client trust list is in production. The hard project-creation blocker is fixed, a polished standalone Quotes module is live, and the Sales Hub now contains Quotes, Retainers, Invoices and Financials as first-class surfaces. Manual retainer hour logging is in place to support the 1 May commercial cutover.

# 2. What is now done

## 2.1 Audit Week 1 stabilise list

Project creation Prisma scopes error — FIXED. All five hubSpotPortal.create call sites now pass scopes:[]. Route handler translates Prisma error codes to user-friendly messages and surfaces validation errors directly.

Wizard Step 1 validation UX — FIXED. Required attributes already in place. Added top-of-step error summary banner. Next button always enabled — clicking with missing fields runs validation and focuses the first invalid field. Auto-suggest project name from client name on blur. Existing-client autocomplete via HTML5 datalist to prevent duplicates.

Session cards not clickable — FIXED. Session rows on project Discovery tab are now Links to /projects/[id]/discovery?session=N with hover state.

Blank client Support form — VERIFIED. Form is fully wired with subject, related project, urgency, description and submit handler. Posts to existing /api/client/support/tickets endpoint. Audit was stale.

Unbranded 404 page — VERIFIED. Branded /not-found.tsx already exists with Muloo logo, copy and routing-aware Back to home button. Audit was stale.

Command Centre vs Projects count consistency — NOT REPRODUCED in this push. Worth re-stress-testing once the new Sales surfaces are live.

## 2.2 Sales Hub buildout (beyond audit scope)

SALES nav group — New top-level navigation group with Quotes, Retainers, Invoices and Financials. Retainers moved out of Delivery — they are recurring revenue, not delivery output.

Quotes pipeline — New /quotes page with status filter chips (Draft, Sent, Approved, Won, Lost, Archived, Superseded), search, status badges and click-through to quote detail.

Quick Quote builder — New single-page builder at /quotes/new with client picker, deal type (fixed/retainer/hybrid), template (one-pager/full), line items table with discount, default rate apply-to-all, content blocks (Muloo intro, exec summary, terms). 600-line focused component, not 3,400-line legacy beast.

Quick Quote renderer — New polished renderer at /quotes/[id] with hero header, quote reference (Q-XXXXXX-Vn), Prepared for/by, Issued/Valid until, Total card with brand gradient, line items with tabular numerals, signature placeholders. Real proposal artefact, ~305 lines.

Quote lifecycle — Status flow: Draft → Sent → Approved → Won/Lost/Archived. Toolbar buttons for Mark Won, Mark Lost, Archive. Edit + Revise (smart: in-place for drafts, new version for sent quotes). Recall action returns sent quotes to Draft.

Template differentiation — One-pager vs Full theme now visually distinct. One-pager hides Muloo intro, tightens spacing, no exec summary heading. Full theme shows everything with more breathing room.

Client-facing portal route — New /client/quotes/[id] route using ClientShell. Authorisation via existing ClientProjectAccess records (client portal user must have access to a project of the same client). Client sees the polished view, not the legacy 3,400-line component.

Internal preview mode — New /quotes/[id]/preview route renders the client-facing layout but loads via internal API (no client portal auth needed). Yellow PREVIEW banner with disabled Approve action so you can sense-check before sharing.

Copy client link — One-click copy of the /client/quotes/[id] URL from the internal toolbar.

Invoices view — New /invoices page with status chip filters, search, three KPI tiles (Outstanding / Paid / Overdue) and link-through to existing invoice detail.

Financials view — New /financials page with four headline tiles (Pipeline, Approved, Won this month, MRR/annualised), six-month won-deals bar chart, quote funnel breakdown with win rate, recurring revenue by client, top clients by combined won + 12-month recurring. Backend loadFinancialsSummary() function pulling live from quote and retainer data.

## 2.3 Retainer ledger and commercial spine progress

Manual retainer hour logging — New POST /api/retainers/:id/log-hours endpoint. Log hours form on retainer detail page (hours, work date, optional description). Auto-creates the period for the work date, runs the same overage protection as the task-based flow, deducts from rollover buckets in FIFO order, writes a MANUAL_ADJUSTMENT ledger entry, audit log. Ready for 1 May commercial cutover.

Retainer delete capability — New DELETE /api/retainers/:id with safety guard. Blocks deletion when sent/paid/overdue invoices exist. Cascades clean periods, ledger entries, rollover buckets, draft invoices.

## 2.4 Client portal improvements

Delivery tab enrichment — Always renders three progress tiles (Currently working on / Progress / Waiting on) sourced from portalSummary. Audit complaint that the tab was just a single link is gone.

Quote approval surface — Client-facing quote view now has prominent Approve quote CTA with confirmation, capture of client portal user name + email + timestamp. Audit ask for first-class quote approval is delivered for the new Quick Quote system.

# 3. Updated phasing against audit recommendation

| Audit Phase | Status | Notes |
| --- | --- | --- |
| Week 1 — Stabilise | COMPLETE | Project create blocker, wizard validation, Support form, 404 page, session cards. Count consistency not stress-tested in this push. |
| Weeks 2-6 — Client trust | PARTIAL | Quote approval screen DONE (via QuickQuote). Delivery tab enrichment DONE. Team access hardening NOT STARTED. Reporting dashboard PARTIAL (Financials shipped, delivery health metrics still to come). Run detail drill-in NOT STARTED. |
| Months 2-3 — Commercial spine | PARTIAL | Manual retainer hour logging DONE. Task-to-ledger automation NOT STARTED. Time tracking MVP NOT STARTED (operator chose to defer). Xero integration NOT STARTED. AI-time at human rate NOT STARTED. |
| Months 4-6 — Scale | NOT STARTED | Utilisation, capacity forecasting, audit log, advanced run telemetry, enterprise access controls. |

# 4. Remaining priorities (next push)

HIGH — HubSpot deal sync (write-only) — Push quote lifecycle status into HubSpot deals. Map QuoteStatus to deal stages. Attach signed PDF as a deal note on approval. Deferred from this push at operator request.

HIGH — Email delivery of quotes — Send polished quote to client via existing Nodemailer setup with portal link. Replaces copy-paste workflow.

HIGH — Server PDF via Puppeteer or Browserless — Replace browser print-to-PDF for consistent A4 output and automated PDF on approval.

HIGH — Team access hardening — Replace admin-set-password with email invite flow. Required before any enterprise or partner onboarding.

MEDIUM — Time tracking MVP — Per-task actual hours capture with timer + manual entry. Operator deferred for now; manual retainer hour logging covers immediate need.

MEDIUM — Xero invoice draft pipeline — Approved-time-to-invoice automation. Requires Xero connection first.

MEDIUM — Run detail drill-in — Token usage, model used, cost per run for AI cost control at scale.

LOW — Version archive and compare UX — Quote version diff and restore. Versioning is at data layer; UX still missing.

# 5. Recommendation

The DeployOS commercial spine is half-built. The retainer ledger now has both task-based approve-to-bill (existing) and manual hour logging (new) in place, supporting the 1 May cutover. The quote tool has gone from a 3,400-line beast that operators avoided to a focused Quick Quote module clients can sign on a polished portal. The Sales Hub gives Jarrud a single home for pipeline, recurring revenue and invoice status.

The next decision point is whether to invest the next sprint in HubSpot deal sync + email delivery (commercial workflow polish) or in time tracking MVP + Xero (commercial spine completion). With manual retainer hour logging already supporting the 1 May cutover, commercial workflow polish is the higher near-term ROI.

End of status update.